## MDR Transmittal
CON-514 TRAIN 1 MDR - TRANSMITTAL & CHECKLIST
Compiled against COV-TEN-CON-514 MDR Index (Rev 0). Mark each item Included / N/A / Outstanding. Issue with SRG Statement of Conformance and Milestone Completion request. ¦ Updated 26/06/2026.
MDR Ref | Section | Document | Status (Included / N/A / Outstanding) | File Reference
1 | Index / Control | MDR Index / Document Register | Included | CON-514_Train1_MDR_Transmittal
2 | Contract / Scope | Scope of Work - Lattice Frame Tower & Stack | Included | Scope of Work (SOW) for Assembly - Erection - Installation of Lattice Frame Tower Structure and Stack
3 | Contract / Scope | Schedule B / Construction Methodology | Included | Construction-Methodology-Schedule-B-Rev-3.2
4 | Contract / Scope | Applicable Standards Register | Included | Applicable-Standards-Register
5 | Drawings | Structural Steel Drawings / Connection Details | Included | COV-6E7BBABE50B8411F967DA64C298EADD2.zip (single zip - all IFC drawings)
6 | Drawings | Stack / Flange Drawings | Included | COV-6E7BBABE50B8411F967DA64C298EADD2.zip (single zip - all IFC drawings)
7 | Procedures | Cranes and Lifting SWMS | Included | SWMS-007-Cranes-and-Lifting
8 | Procedures | EWP Operations SWMS | Included | SWMS-004-EWP-Operations
9 | Procedures | Materials Handling Equipment SWMS | Included | SWMS-005-Materials-Handling-Equipment
10 | Procedures | Rope Access Operation SWMS | Included | SWMS-006-Rope-Access-Operations
11 | Procedures | SRG WHS Management Plan | Included | WHS-Management-Plan-COV-MMP-0001-signed
12 | Procedures | Working at Height Procedures | Included | Working at Heights
13 | Procedures | Bolting / Torquing / Tensioning Procedure | Included | COV-TEN-CON 514 - Stack Raise Works Bolt Tension/Torque Settings.pdf
14 | Procedures | Flange Management / Stack Flange Torque Procedure | Included | COV-TEN-CON 514 - Stack Raise Works Bolt Tension/Torque Settings.pdf
15 | Procedures | Survey Methodology | Included | J17355-SRG COV-TEN-CON 514 - Survey Report 21
16 | ITPs | ITP - Module Assembly | Included | 16_ITP-Module-Assembly
17 | ITPs | ITP - Module Installation | Included | 17_ITP-Module-Installation
18 | ITPs | ITP - Stack Removal & Installation | Included | 18_ITP-Stack-Removal-and-Installation
19 | ITPs | ITP - Existing Flange Removal & Installation | Included | 19_ITP-Existing-Flange-Removal-and-Installation
20 | ITPs | ITP - Painting & Blasting | Included | 20_ITP-Painting-and-Blasting
21 | Material Records | Grout Product Data / Batch Records | Included | Fosroc_Conbextra_GP_TDS
22 | Material Records | Welding Consumable Certificates | Included | 3.2 Welding Rods Cert E7016 & ER70S-6 Tig Wire
23 | Material Records | Painting Interbond 1202 PDS | Outstanding
24 | Bolting QA | Bolt Register | Included | 24_Bolt-Register
25 | Structural Inspection QA | Structural Splice / Gusset / Fishplate Checklist | Included | 25_Structural-Splice-Gusset-Fishplate-Checklist_Module-1 & 25_Structural-Splice-Gusset-Fishplate-Checklist_Module-2 & 25_Structural-Splice-Gusset-Fishplate-Checklist_Module-3
26 | Structural Inspection QA | Stack Flange Connection Checklist | Included | 26_Stack-Flange-Connection-Checklist
27 | Paint & Blast QA | Surface Preparation Report | Outstanding
28 | Paint & Blast QA | Ambient Condition Report | Outstanding
29 | Paint & Blast QA | Coating Report | Outstanding
30 | Lift Study | Lift Studies | Included | Lift-Study-Cranecorp-T1-Module-1 & Work-Pack-Covalent-Stack-Removal-Rev-A & Work-Pack-Mancage-Access-Rev-A
31 | Survey Records | Survey Method Statement | Included | Survey-Method-J17355-Rev-2
32 | Survey Records | Survey Report - Module 1 | Included | Survey-Report-J17355-01 & Survey-Report-J17355-02 & Survey-Report-J17355-03 & Survey-Report-J17355-08
33 | Survey Records | Survey Report - Module 2 | Included | Survey-Report-J17355-10
34 | Survey Records | Survey Report - Module 3 | Included | Survey-Report-J17355-12 & J17355-SRG COV-TEN-CON 514 - Survey Report 12 rev1
35 | Survey Records | Survey Report - Module 4 | Included | J17355-SRG COV-TEN-CON 514 - Survey Report 13 rev1
36 | Survey Records | Survey Report - Module 5 | Included | J17355-SRG COV-TEN-CON 514 - Survey Report 14 & J17355-SRG COV-TEN-CON 514 - Survey Report 14 rev1
37 | Survey Records | Survey Report - Stack 1 Flange | Included | Survey-Report-J17355-09
38 | Survey Records | Survey Report - Train 1 Stack As-Built | Included | J17355-SRG COV-TEN-CON 514 - Survey Report 20
39 | Survey Records | Survey Report - Train 1 Tower As Built | Included | J17355-SRG COV-TEN-CON 514 - Survey Report 22 & J17355-SRG COV-TEN-CON 514 - Survey Report 22.1
40 | Grouting Records | Grout Strength Test Reports | Included | Grout-Compressive-Strength-Train-1-14day-398-R-26-16243-1
41 | Welding / NDT | WPS / PQR Register | Included | PQR 283 R0 Complete GTAW & MMAW A106 & WPS 283 R2 SRG Global GTAW & MMAW A106 - Copy
42 | Welding / NDT | Weld Traceability Record | Included | Welder Traceability Record
43 | Welding / NDT | Welder Qualification Records | Included | 244660-3-1_RT_Welds_R2 & 244660-4-1_RT_Welds_R2
44 | Welding / NDT | Weld Map | Included | Stack A weld map T1
45 | Welding / NDT | NDT Reports | Included | 244602-5-1_RT_Welds_R5 & 244602-4-1_MT_R5
46 | Calibration | Welding Equipment Calibration Certificates | Included | 20260519-02
47 | Calibration | Survey Equipment Calibration Certificates | Included | Leica MS50 368956 Calibration Report
48 | Calibration | Testing Equipment Calibration Certificates | Included | Tool Calibration Register