## Cover Page
Instructions for Use
Column Name for Risk Registers | Action Required | 1 | Risk review must be conducted with - The TAP Owner and/or Delegate - Safety Representative - Executive Management Team Rep - Line Management Team Rep - HSE Team member
Risk ID | Auto generated when creating a new line | 2 | All reviews must be captured under the Version Review tab
Category | Pick from drop down list | 3 | Any risk level at with a score of 16 and above must be escalated to the HSE Manager
Risk Type | Pick from drop down list | 4 | To create a new line at the end of the table, please drag the arrow down at the right end corner of the Risk Register table
Activity | Complete by dot point as detailed as practicable | 5 | The Hazard Sub-Type tab can be used for reference
Hazard | Complete by dot point as detailed as practicable | 6 | The Risk Register to be reviewed are: - Critical Risk - Contruction Activities - Mt Holland - KWI
Risk | Complete by dot point as detailed as practicable
Site Applicable to | Pick from drop down list
Consequence Category (Inherent) | Pick from drop down list
Consequence (Inherent) | Pick from drop down list
Probability (Inherent) | Pick from drop down list
Inherent Risk Level | Auto generated values
Inherent Risk Score | Auto generated values
Existing Controls in place | Complete by dot point as detailed as practicable
Consequence Category (Residual) | Pick from drop down list
Consequence (Residual) | Pick from drop down list
Probability (Residual) | Pick from drop down list
Residual Risk Level | Auto generated values
Residual Risk Score | Auto generated values
Treatment Action Plan | Complete by dot point as detailed as practicable
TAP Status | Pick from drop down list
TAP Owner (Accountable) | Name of Covalent Employee
TAP Delegate (Responsible) | Name of Covalent Employee
Date Endorsed | Date risk review conducted and endorsed
Date of next Review | Date set for next review of current risk as per below guide - Open Risk - as follows: 25% - Weekly 50% - Fortnightly 75%/Ongoing - Monthly Closed Risk - Quarterly

## Version Review
Initial Review Date
Review Team
Date of Establishment
Date of Review | Risk ID Reviewed | Register Reviewed | TAP Owner | TAP Delegate | HSR | Executive Team | Line Management | HSE Team | Comments | Escalation Required | Escalated to

## Risk Matrix
Covalent HSE Risk Matrix
Covalent Lithium Project Execution Risk Prioritization Matrix
|  |  | Risk Class: | Low | Medium | High | Extreme
Likelihood Descriptions & Index |  |  |  | Qualitative Risk Level (QRL)
|  |  |  | Insignificant | Minor | Moderate | Major | Severe
The event is expected to occur in most circumstances |  | Almost Certain (>80%) |  | 11 | 16 | 20 | 23 | 25
The event will probably occur in most circumstances |  | Likely (50-80%) |  | 7 | 12 | 17 | 21 | 24
The event is expected to occur at some time | 3 | Possible (25-50%) |  | 4 | 8 | 13 | 18 | 22
The event could credibly occur at some time |  | Unlikely (1-25%) |  | 2 | 5 | 9 | 14 | 19
The event occurs infrequently, if ever in like industries |  | Rare (<1%) |  | 1 | 3 | 6 | 10 | 15
|  | Consequences Indices & Description |  | 1 | 2 | 3 | 4 | 5
|  |  |  | Insignificant | Minor | Moderate | Major | Severe
| Health & Safety |  |  | Minor injury or illness (first aid) | Medical treatment or restricted duties injury or illness | Lost time injury or illness | Critical injury / permanent disability | One or more fatalities
| Environment |  |  | Minor environmental impact, managed within operating budgets | Localised environmental impact requiring AUD 20K or more to correct | Short term (< 1 yr) environmental impact requiring up to AUD 100K to correct | Serious medium-term (1 - 5 yrs) environmental impact, requiring AUD 1M to AUD 5M to correct | Widespread long-term environmental damage (> 5 ys), requiring > AUD 5M to study or correct in penalties
| Regulatory |  |  | Breach of internal target or objective | Breach of corporate standard, internal limit or external guideline | Breach of licenses or regulation | Infringement or fine. Enforcement action from the regulator | Regulatory intervention or prosecution with potential Loss of operating license
| Reputation |  |  | Reference to community consultation group; public or customer awareness exists, no public concern | Adverse publicity in local media; concerns on performance raised by shareholders, government, community or customers | Adverse publicity in State/Regional media; decrease in political, shareholder, community or customer support | Damage to Corporate reputation at the National level; significant decrease in political, shareholder, community or customer support | Damage to Corporate reputation at International level; Major loss of political, shareholder, community or customer support
| Production Impact (% deviation from planned LiOH production in first 2 yrs of operation) |  |  | <1% of planned LiOH production | 1 - 5% of planned LiOH production | 5 - 10% of planned LiOH production | 10 - 30% of planned LiOH production | > 30% of planned LiOH production
| Schedule (Impact to RFSU or Key Project Milestone) |  |  | < 1 week | 1 to 2 weeks | 2 weeks to 6 weeks | 6 weeks to 4 months | > 4 months
| Financial (CAPEX or NPV) |  |  | < AUD 500k | AUD 500k to AUD 5M | AUD 5M to AUD 20M | AUD 20M to AUD 60M | > AUD 60M

## Hazard Sub-Type
Hazard Sub Type
Type | Description
Aesthetics | Physical attributes, e.g. size, shape, colour and appearance
Air | Emissions to air, dust, vapours, air pollution, abrasive blasting, gas release
Biomechanical | Manual handling, potential for muscles to be excessively pushing, pulling, holding, restraining loads or repetitive work
Biological | Bodily fluids, bacteria, viruses, insects, plants, fungi, animals
Chemical | Inhalation, absorption, ingestion of a liquid, gas, dust or substance, or may cause explosion, fire or long term chronic illness
Electrical | Contact with electrical energy
Energy | Gas usage, electricity usage, energy efficiency, diesel usage
Environment | Contaminated flaura, acid sulphate soils, bushfire, soil pathogens (dieback), hygiene & cleanliness (vehicle, plant), artefacts / heritage, contamination, excessive or inefficient water use, non-compliance with utilities licence, Conservation area works or monitoring, weeds, feral animals, hygiene & cleanliness (vehicle, plant), protected flora, protected fauna
Ergonomic | Manual handling, incorrectly designed workstations, audio and visual alarms, colour coding mechanisms
Gravitational | Fall from heights or objects falling from heights, slip/trip/falls on same level, collision/impact to personnel/equipment/building
Lighting | Inadequate or insufficient lighting
Mechanical | Plant, equipment and items with potential to cut, rip, tear, abrade, crush, penetrate, produce projectiles or cause sudden impact
Noise | Exposure or potential exposure to constant or excessive noise
Pressure | Boilers, gas cylinders, compressed air
Psychosocial | Stressful relationships or interactions, traumatic event, bullying, work intensification
Radiation | UV, lasers, telecommunications, electromagnetic
Raw Materials & Natural Resources | Stewardship, sustainability, lifecycle assessment, packaging and transportation
Thermal | Hot or cold environment, hot objects, fire, welding, hot or cold processes, cool rooms
Vibration | Exposure or potential exposure to vibration
Waste & By-Products | Littering, waste contamination, poor waste management, accumulation of waste materials
Work Environment | Interaction with the work environment, building structure/layout/design, workflow/traffic management (personnel,plant, equipment), obstacles, furniture and fittings.
Other | Any other hazard that may not be defined above

## Critical Risk
Covalent Critical Risk Register
[8 empty] | Inherent Risk Assessment | [6 empty] | Residual Risk Assessment
Activity | Risk ID | Category | Risk Type | Activity | Hazard | Risk | Site Applicable to | Consequence Category (Inherent) | Consequence (Inherent) | Probability (Inherent) | Inherent Risk Level | Inherent Risk Score | Inherent Risk Rating | Existing Controls in place | Consequence Category (Residual) | Consequence (Residual) | Probability (Residual) | Residual Risk Level | Residual Risk Score | Residual Risk Rating | Treatment Action Plan | TAP Status | TAP Owner (Accountable) | TAP Delegate (Responsible) | Date Endorsed | Date of next Review
10000 20000 | CR-01 | Safety | Critical | Confined Space Entry | • Hazardous substances • Lighting • Work Environment • Use of energised equipment in a confined space • Conducting hot work in a confined space | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | • Confined Space Entry Rescue Plan developed in accordance with AS2865 • Confined Space Entry Permit (Permit to Work system to be in place and used for all confined Space entry activities) • Confined Spaces Procedure • Confined Space Register • Critical Risk Management Standard Templace - Standard 6 - Confined Spaces Critical Control Verification • Confined Space Rescue - Trigger Response Plan Guideline (Tarp) ' Forced ventilation where required, - Ventilation developed in accordance with AS2865and rescue plan - Confined space entrants wear a harness (as assessed) to facilitate rescue in the event of an emergency. - Gas testing prior to entry to confined space and continuously when in a confined space - JHA to include Work in Restricted Work Spaces activities, risks, permitting requirements and controls. Use of energised equipment in a CS: '- Isolation Procedure - SWMS to include Work in Restricted Work Spaces activities, risks, permitting requirements and controls. - Permit to Work system to be in place and used for all confined Space entry activities. - Test for Dead Conducting hot work in a confined space: '- Gas testing prior to entry to confined space and continuously when in a confined space - Forced ventilation where required | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 75% | EAS Manager | H&S Managers
| CR-02 | Safety | Critical | Working at Height | • Climatic natural events • Gravitational • Work Environment | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | • Working At Height Rescue Plan Form • Working At Height Permit • Working At Height Fall Injury Prevention System (Fips) Register • Critical Risk Management Standard Template - Standard 4 - Working At Heights • Heights Rescue - Trigger Response Plan Guideline (Tarp) '- No scaffolding activities to take place during high winds and storms - Extreme Weather management plan includes steps for removal of scaffold planks in the event of a cyclone and inspection before reinstatement. Grid mesh inspection on handover of the task completion, - Grid mesh to be secured with huck bolt / proprietary clip in all four corners as a minimum - Grid mesh removal process/ permit '- All rope access personnel must have in-date IRATA certification - Use only certified and recognised anchor points (15kn rated) ICOP Part 2 - Section 2.7.9, Part 3 - Annex F, Contractor RA operational Procedure Section 19 - Rope Access Pre-start checklist have been completed - SWMS, Rescue Plan and 5x5 has been developed agreed and in place - All rope access equipment shall undergo a pre-use and 6 monthly detailed inspection - Adhere to Contractor rope access operational procedure and IRATA International Code of Practice (ICOP) - WAH procedure in place - PTW system in place | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 50% | EAS Manager | H&S Managers
| CR-03 | Safety | Critical | Cranes and Lifting | • Climatic natural events • Gravitational • Work Environment | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | • Cranes and lifting register • Covalent lithium crane assembly checklist • Non-slewing crane theory and practical assessment • Non-slewing crane assessor guide • Vehicle loading crane theory and practical assessment • Vehicle loading crane assessor guide • Critical risk management standard templace - standard 5 - cranes and lifting • Critical lift plan to be reviewed/approved by Area Authority '-Overload protection on the cranes - Lifting charts in all crane cabins - Job planning includes lift plan - Designated crane radio channel in place - Communication to all nearby workgroups - planned activities in the area - Personnel cage procedure and approvals: Certified and registered Personnel cage includes tags and SWL - Daily pre-start checks & recording systems - Manufacturers test certification to accompany all lifting and rigging equipment. - Visual inspections to be conducted prior to each use of all lifting equipment including lifting lugs - Registration, certification, annual inspection, testing and maintenance documentation required prior to mobilisation of lifting and rigging equipment. - Adequate storage facility provided for all lifting equipment - Lifting equipment to be inspected at 3 monthly intervals by a competent person, tagged and documented in a Rigging Register. " - High Risk License for all crane operators, dogman and riggers and Verification of competency - Permit to work as determined by the lifting category - Designated SME and or qualified supervisor to determine the methods, equipment and develop plans for all lifting - Ticketed and VoC’d riggers and dogman - Engineered lifting frames for regular lifts - Daily weather forecast at prestart included in job planning - Wind speed cut off for crane operations - Positive Communication – Lifting activity stops if communication lost occur - Designated crane radio channel in place (as assessed)." - Spotters to be considered on all occasions during operations. - SWMS to include Crane activities, congestion risks and controls. - Designate a qualified SME and or supervisor to determine the methods, equipment and develop plans for all lifting operations. - Critical lift procedure to be reviewed/approved by Area authority" - Ticketed and VOC crane operator with Personnel cage experience" - Critical Lift Procedure - Personnel cage Procedure - Ticketed and VOC crane operator with Personnel cage experience" - Permit to Work for man cage operations | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Ongoing | EAS Manager | H&S Managers
| CR-04 | Health | Critical | Vehicles and Driving (includes JMP) | • Ergonomics • Personal Behaviour • Lighting • Vehicular energy • Breakdown of communication between drivers • Mechanical failure of vehicle • Speeding • Environmental conditions (including extreme weather) • Congested work area • Unexpected movement of vehicle (e.g. swerving) • Poor loading practices | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | • Light vehicle operation verification of competency • Light vehicle compliance inspection checklist • Light vehicle prestart check • Light vehicle inspection form • Light vehicle/truck inspection form • Light vehicle operation procedure • Vehicle and driving procedure • Light vehicle theory and practical VOC • Light vehicle theory assessor guide • Critical risk management standard template - standard 3 - vehicles and driving critical control verification 'Drivers licenses reviewed and entered into training records. - Site Assessment of drivers & onsite verification of competency. - Regular reviews and updates to licence expiry dates - D&A testing regime in place - Adherance to FFW and Fatigue protocols. -Traffic management plan - site road design & parking layout. - Site signage - Inductions & expectations reinforced - Health and safety management plan, VOC and Licensing requirements. - Journey Management Plans as assessed or for those driving distance. - Work place inspections, Task Obs. - Active monitoring of fatigue through workhours, rostered and employee awareness - Daily pre-start inspection on vehicle '- Road signs in place - Regulated speed and minimise vehicle movement, monitor and assess. - Traffic Management Plan '- Weather Reports - Traffic Management Plan - Lighting plants installed where required - Change in speed limit between day and night - Restrictions on moving equipment at dawn and dusk to reduce interaction with wildlife - SIMSOPS review prior to starting work '-Heavy vehicles are secured as per OEM requirements (chocks for parking if assessed.) - Reverse parking all vehicles so forward moving on leaving parking - first movement forward | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-05 | Safety | Critical | High Voltage Management | • Electrical energy • Personal Behaviour • Quality | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | • Electrical safety management plan • Electrical tag and test register • Appointment letter - electrical supervisor • Critical risk management standard template - standard 2 - electrical safety - Guarding on all equipment - Over speed on high speed rotating equipment | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-06 | Safety | Critical | Dropped Objects | • Climatic natural events • Gravitational • Work Environment | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - Tools & materials to be adequately secured to prevent falling. - Personal tool lanyards (Secondary securing mechanisms) to be utilised. '- JHA to be completed to determine dropped object risks and controls. - Barricade off the area below the work - Edge protection with exclusion zones and/or overhead protection as a secondary means of control. - Drop mats for extended work practices '- Permit to work includes hand back process which confirms that site is returned to original condition and clear of tools - Supervision - Workplace pre start and periodic inspection '- Tool bags - Use of Gin Wheels, cranes, cages '- Exclusion zones established underneath all rope access working areas - All tools must have a lanyard which attached to a secure point on the harness or suspended on a separate ropes. Over 8Kg tools must be suspended independently from the user. ICOP Part 3 - Annex M, Contractor rope access operational procedure Section 17.1 | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-07 | Health | Critical | Hazardous Substances | • Hazardous substances • Natural Environment | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | • Hazardous chemical application form • Hazardous material management procedure • Hazardous chemical register • Mt holland & refinery - hazardous materials management procedure • Theft of detonators and explosives, hazardous chemicals, plant equipment and fuels - trigger response plan guideline (tarp) • Hazardous materials plan - liberty industrial 'Read and understand SWMS - Product/Chemical Risk Assessment and SWMS to determine the need for the substance and if it can be substituted for a safer product. - Ensure the area is well ventilated. - PPE appropriate for the product and Job to be worn at all times and adequate ventilation when working in areas of limited ventilation. - Eliminate all ignition sources such as cigarettes, flames, mobile phones from storage areas. - Chemical approval process -SDS available at the location of works 'Cylinders secured on vehicles when transported, cages for transportation - Cylinders transported in purpose built trolleys - Compliance with AS 4332-2004 (The storage and handling of gases in cylinders). - Cylinders to be stored in upright position in a racking system using a non abrasive, coated chain to hold in position. '-Bunding - storage and generator (Infrastructure design at refinery to AS) -Operational controls -Interlock generator operation with diesel storage feed pump -Spill kits and training in use. -Pre start regular inspections -Inspection of plant & full commissioning -Concrete/ dedicated bunded usage and or refuelling areas. -Work place inspections, Task Obs, Availability of SDS. Chemalert and following site access requirements and controls. - Ensure LPG storage area is provided which complies with DG requirements (including exclusion of ignition sources, separation distances, etc.) | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-08 | Safety | Critical | Entanglement and Crushing | • Gravitational • Mechanical Energy • Work Environment | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - Adequate and compliant Barriers. - Controls as per safety plan/JHA/SWMS - Permit to work - working at height, Spotters - Training in W@H, Scaffolding, Crane usage and EWP usage - PPE - fall restraint, fall arrest, fall prevention correct & maintained. - EWP fitted with correct proximity devices. - Work place inspections and task observations conducted - Compliance to AS 1657, AS1892, AS4576 | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-09 | Safety | Critical | Excavations and Penetrations | • Climatic natural events • Gravitational • Work Environment | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | • Excavation and penetration permit • Excavation and penetration procedure • Critical risk management standard template - standard 9 - ground disturbance and excavations critical control verification '- JSA to include earthworks activities, risks and controls. - Excavation and Surface Penetration Risk assessment - GIS drawings for known services - Hand digging around buried services - Excavation permit - P&ID reviewed as part of the excavation activity - Pipe work is above ground on site except for under roads - Isolation procedure for pipe work change out - Excavation and Surface Penetration Risk assessment. '- Work area to be appropriately barricaded, delineated to prevent unnecessary traffic, plant or personnel in accordance with Site Traffic Management Plan. - Appropriate signage to be used on all approach sides. All services terminated. Review all in-ground drawings available prior to each excavation task. -Use a spotter when digging to identify any in-ground identifiers of services before impact. -Management of the excavation via barricading and signage. -Task JHA/SWMS, Work place inspections, Task Obs. - Operators to have necessary tickets and VOCs in place prior to commencement of task. - Hand digging around buried services" - Regular inspections of excavations - escape path put in place for fauna - Fauna barricades put in place - Engineers define shoring requirements - Excavation sides to be appropriately shored - Confined space permit if greater than a specified depth (AS2865) or deemed to be a confined space" - Excavation and penetration certificate - Exit ramps for all trenches left overnight - Auger holes capped at night - Trench fauna inspection for all trenches - Work area to be appropriately barricaded, delineated to prevent unnecessary traffic, plant or personnel in accordance with Site Traffic Management Plan. | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-10 | Safety | Critical | Hazardous Energy | • Electrical Energy • Gravitational Energy • Mechanical Energy • Pressure • Radiation Energy •Thermal/Fire/Explosion - Use of faulty/damaged equipment, - Unknown energy source. - Poor electrical installations - Inexperienced personnel - Unauthorised equipment being used - Unauthorised modification to electrical equipment - Poor storage and lack of maintenance. - Incorrect equipment / tool used for the task. - Equipment's not isolated correctly - Equipment / tool used in the incorrect manner. - Working on live equipment e.g., fault finding activities - Incorrectly isolated equipment - Inexperienced personnel - Personnel taking shortcuts | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | • Critical Risk Management Standard Template - Standard 1 - Exposure To Hazardous Energy Critical Control Verification 'Permit to work system - Isolation Procedure - Lock out/tag out - P&ID include identification of the equipment - Isolation verification for each isolation by competant for the maintenance personnel - Isolation list includes all isolations that have been done - Isolation tags for each isolation point (matches the permit number) - approved isolation authority personnel undertake isolation and the tagging of equipment. '- All electrical installations and equipment shall comply with AS/NZS 3000-2007 electrical requirements. '- All tools and equipment that are used shall be maintained in accordance with manufacturers recommendations, have required guards in place, and are in good working order. '- Visual inspection prior to use to ensure integrity, guards are attached and quarterly tag affixed. - Quarterly testing and tagging as per statutory requirements. - All tools and equipment that are used shall be maintained in accordance with manufacturers recommendations, have required guards in place, and are in good working order. - Dedicated tool storage. -All works to be conducted by licensened tradesperson (electricians, etc.) -Drawings of all delivered electrical equipment reviewed prior to energisation. -Correct equipment and PPE available and in-use for HV work. - Electrical Plant register to be maintained to identify all equipment subject to quarterly inspections. - Inspections by qualified electrical tradespersons and defective items placed out of service until fixed. - VRD's on all welding machines. - Visual inspection of all electrical equipment prior to use" - Earth breaker protections on all 240 v outputs and inspected as per schedule. - Electrical installations by qualified electrical tradespersons only. - All electrical installations and equipment shall comply with AS/NZS 3000-2007 electrical requirements. " - Electrical installations by qualified electrical tradespersons only. - Inspections by qualified electrical tradespersons and defective items placed out of service until fixed. - No unauthorised equipment on site - Defective items placed out of service until fixed. - Experienced competent / qualified electrical personnel (VoC'd) . | Health & Safety | Severe | Rare | Medium | 15 | Medium 15 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-11 | Safety | Critical | Hot Works | • Ergonomics • Lighting • Radiation energy | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | • Hot work permit • Hot work procedure • Designated hot work area register | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-12 | Health | Critical | Psychosocial | • Work environment | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - EAP - Mates at Work - DMIRS Audit - Mental Health First Aid for supervisors - Toolbox topic on mental wellbeing (daily) - Mental Health campaigns (R U OK) | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-13 | Safety | Critical | Explosives | • Noise and vibration • Pressure • Thermal/Fire/Explosion energy | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | • Theft Of Detonators And Explosives, Hazardous Chemicals, Plant Equipment And Fuels - Trigger Response Plan Guideline (Tarp) | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-14 | Environment | Critical | Slope Failure | • Climatic natural events • Gravitational • Work Environment | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | • Procedures and Permits shall be in place, communicated and followed. • Geotechnical design implemented into slope construction plan • Geotechnical inspections and monitoring systems. • Regular inspections & monitoring of tailings & water storage facilities, pit walls & crests, stockpiles & dumps • Ground Control Management Plan • Competent & Qualified Geotechnical Engineer • Barricades shall be erected as per Statutory and Project requirements Including the use of warning signs/tags | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-15 | Safety | Critical | Heavy Mobile Equipment | • Climatic natural events •Lighting • Mechanical Energy • Personal behaviour • Work environment | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - Health and safety management plan - Permit to work - Lifting plans - Training and VOC - Register of itinerant classified plant. - Work place inspections, Task Obs '- Three point of contact, access plant facing forward, - No items to be carried accessing/egressing SME - Pres-start check on SME( check condition of steps and handrails, remove mud,etc.) - Communication / familiarisation of area, change management processes, inspection of area, competent operators, signage, call up points, pits permit - Monitoring, inspection of area, competent operators who can identify ground conditions, windrows / edge protection, exclusion zones - Tyre management plans and monitoring of tyre condition / temperature - Ergonomic assessment, seating design and plant maintenance, job rotation | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers
| CR-16 | Safety | Critical | Traffic Management | • Climatic natural events • Lighting • Mechanical Energy - Breakdown of communication between personnel - Failure to delineate the worksite - Congested work areas - Distracted pedestrians - Blind corners around the worksite - Poor parking practices (parking too close to work area) | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - Positive Communications between personnel - Barricading around the worksite - Spotter for any heavy vehicle movement in congested areas - Designated pedestrian areas - Job planning - Prestart meetings - Barricading around work areas and signage - Barricading around process equipment near roads - Adherence to mobile phone approval and use on site - Positive Communications between personnel - Barricading around work areas and signage - Barricading around process equipment near roads - Traffic Management Plan - Designated parking areas | Health & Safety | Severe | Unlikely | High | 19 | High 19 |  | Actions in Progress - 25% | EAS Manager | H&S Managers

## TBRA
Stack Extension - Structural frame build & stack installation
SOW: Installation of structural frame and stack extension to 97m (SRG Global) 21 May - 15 Jun
Activity | Risk ID | Category | Risk Type | Activity | Hazard | Risk | Site Applicable to | Consequence Category (Inherent) | Consequence (Inherent) | Probability (Inherent) | Inherent Risk Level | Inherent Risk Score | Inherent Risk Rating | Existing Controls in place | Consequence Category (Residual) | Consequence (Residual) | Probability (Residual) | Residual Risk Level | Residual Risk Score | Residual Risk Rating | Treatment Action Plan | TAP Status | TAP Owner (Accountable) | TAP Delegate (Responsible) | Date Endorsed | Date of next Review
| R-01 | Safety | Operational | Pre-mobilisation - Induction, PTW, PH and Site Famil
10000 20000 | R-02 | Safety | Critical | Mobilise people, equipment and office containers, |  | Delay in mobilising people, plant & equipment | KWI | Schedule | Major | Possible | High | 18 | High 18 | - Portable offices to be inspected and approved by COV electrical dept, - Laydown yard has been allocated by Covalent, - Vehicles and mobile equipment to be mobilised including: vans, 3 x utes, telehandler, franna - people mobilisation - site induction, Permit holder training, site famil to be completed, **clarify if contract supervisor can do site famil?** - **PPE requirements - **email PPE site maps (Deepak)** - **Chemical boots - exemption is to be given by Craig & Chris (COV)** - **DAP training required. DAP will be provided by COV. - **Radios to be provided by COV (Craig)** | Health & Safety | Moderate | Possible | Medium | 13 | Medium 13 | - Portable offices to be inspected and approved by COV electrical dept, - Laydown yard has been allocated by Covalent, - Vehicles and mobile equipment to be mobilised including: vans, 3 x utes, telehandler, franna - people mobilisation - site induction, Permit holder training, site famil to be completed, **clarify if contract supervisor can do site famil?** - **PPE requirements - **email PPE site maps (Deepak)** - **Chemical boots - exemption is to be given by Craig & Chris (COV)** - **DAP training required. DAP will be provided by COV. - **Radios to be provided by COV (Craig)**
| R-03 | Safety | Critical | Job setup | moving traffic, plant operational. | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Major | Possible | High | 18 | High 18 | - barricading, exclusion zone. Roads around calciners 1&2 and acid roasts 1&2. - when crane boom is down, road needs closed 120m (between calc1 and AR2) - Planning meeting 7am daily to discuss SIMOPS. - crane lowers when 9.8m/s wind speed. - Crane operations only on D/S. - **Need laydowndown area for crane - COV (Deepak) - Modules 1-3 uses smaller crane (130t) - set exclusion zone for the steel frames. - no underground services - already checked during civil works - above ground services - - **Deepak to provide drawings on services (under and above ground) - ground compaction test has been done. **Deepak to provide Traffic: - traffic for 3.5m length, 3m height - clearance is okay, designated pathway? - Deepak to provide Traffic Flow Diagram - enter gate 1, go on ring road, turn into calciner road. - **Thanes to provide traffic diagram and Craig to review (for truck traffic flow) - Truck driver will be escorted. or complete induction. - One day notice to gatehouse - for any deliveries. Provide how many trucks and content, | Health & Safety | Moderate | Unlikely | Medium | 9 | Medium 9 | - barricading, exclusion zone. Roads around calciners 1&2 and acid roasts 1&2. - when crane boom is down, road needs closed 120m (between calc1 and AR2) - Planning meeting 7am daily to discuss SIMOPS. - crane lowers when 9.8m/s wind speed. - Crane operations only on D/S. - **Need laydowndown area for crane - COV (Deepak) - Modules 1-3 uses smaller crane (130t) - set exclusion zone for the steel frames. - no underground services - already checked during civil works - above ground services - - **Deepak to provide drawings on services (under and above ground) - ground compaction test has been done. **Deepak to provide Traffic: - traffic for 3.5m length, 3m height - clearance is okay, designated pathway? - Deepak to provide Traffic Flow Diagram - enter gate 1, go on ring road, turn into calciner road. - **Thanes to provide traffic diagram and Craig to review (for truck traffic flow) - Truck driver will be escorted. or complete induction. - One day notice to gatehouse - for any deliveries. Provide how many trucks and content,
| R-04 | Safety | Critical | Train 1 - Install structural frame module 1 | Cranes & lifting - dropped objects, suspended loads, Hot work - fire risks SIMOPS - calciner operational | Cranes & Lifting: • Critical Injury • Permanent disability • One or more fatalities Demolition: - SIMOPS, - interaction with traffic & HMEs | KWI | Health & Safety | Severe | Possible | High | 22 | High 22 | - Lifting plan to be reviewed/approved by Covalent Representative. - Designated SME and or qualified supervisor to determine the methods, equipment and develop plans for all lifting - PTW stage 1 - no isolation, stage 2 - with isolation. - 30 people working at once. - COV to setup remote lockbox in the field. - T2 stack extension - date from 22 Jun & planning **Raj to plan with Garth/Chris - Overload protection on the cranes - Designated crane radio channel in place (separate radio channel between crane operator, rigger and spotter) - Positive Communication – Lifting activity stops if communication lost occur - Adequate barricading & exclusion zone - High Risk License for all crane operators, dogman and riggers and Verification of competency - Personnel cage procedure and approvals: Certified and registered Personnel cage includes tags and SWL - Daily pre-start checks & recording systems - Manufacturers test certification to accompany all lifting and rigging equipment. - Visual inspections to be conducted prior to each use of all lifting equipment including lifting lugs - Registration, certification, annual inspection, testing and maintenance documentation required prior to mobilisation of lifting and rigging equipment. - Adequate storage facility provided for all lifting equipment - Lifting equipment to be inspected at 3 monthly intervals by a competent person, tagged and documented in a Rigging Register. " - Daily weather forecast at prestart included in job planning - Wind speed cut off for crane operations (9m/s) - Spotters to be used on all occasions during operations. - SWMS to include Crane activities, congestion risks and controls. | Health & Safety | Severe | Unlikely | High | 19 | High 19 | - Lifting plan to be reviewed/approved by Covalent Representative. - Designated SME and or qualified supervisor to determine the methods, equipment and develop plans for all lifting - PTW stage 1 - no isolation, stage 2 - with isolation. - 30 people working at once. - **COV to setup remote lockbox in the field (Chris Calvert) - T2 stack extension - date from 22 Jun & planning **Raj to plan with Garth/Chris
| R-05 | Safety | Critical | Train 1 Install module 2. | Cranes & lifting - dropped objects, suspended loads, EWP. Hot work Traffic - interactions with vehicles/ pedestrians | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Possible | High | 22 | High 22 | - Uneven ground. Gas line above. - **Crane Corp - confirm on crane location & develop lifting plan. COV to review and approve. - Gas line into ARC - barricade around gas lines to prevent interactions - Need info - all services in the area - **Deepak to provide drawings for all services under and above ground. - Preassembly on western side of the stack. -Traffic management plan - site road design & parking layout. - Site signage - Inductions & expectations reinforced - Drivers licenses reviewed and entered into onboarding records. - D&A testing regime in place - Adherance to FFW and Fatigue protocols. - Health and safety management plan, VOC and Licensing requirements. - Work place inspections, Task Obs. - Daily pre-start inspection on vehicle - Regulated speed and minimise vehicle movement, monitor and assess. - SIMOPS review prior to starting work | Health & Safety | Severe | Unlikely | High | 19 | High 19 | - Uneven ground. Gas line above. - **Crane Corp - confirm on crane location & develop lifting plan. COV to review and approve. - Gas line into ARC - barricade around gas lines to prevent interactions - Need info - all services in the area - **Deepak to provide drawings for all services under and above ground.
| 4 | Safety | Critical | Train 1 Deconstruct the stack (above 1st flange) | Cranes & lifting - dropped objects, suspended loads, Working at heights, Dropped objects | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | All of the above | Health & Safety | Severe | Unlikely | High | 19 | High 19
| 5 | Safety | Operational | Train 1 Preassembly module 3, | Cranes & lifting - dropped objects, suspended loads, Work at Height - Dropped objects - SIMOPS - shutdown activities around | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - Preassembly on eastern side, - uneven ground - **Deepak - level the ground & put the plate (SRG) - W@H, EWP, pipe rack nearby - Heights Rescue - Trigger Response Plan Guideline (Tarp) - All rope access personnel must have in-date IRATA certification - Use only certified and recognised anchor points - Rope Access Pre-start checklist have been completed - SWMS, Rescue Plan and 5x5 has been developed agreed and in place - All rope access equipment shall undergo a pre-use and 6 monthly detailed inspection - Adhere to Contractor rope access operational procedure and IRATA International Code of Practice (ICOP) | Health & Safety | Severe | Unlikely | High | 19 | High 19
| R-08 | Safety | Critical | Train 1 Stack demolition | Cranes & lifting - dropped objects, suspended loads, Work at Height - Dropped objects - SIMOPS - shutdown activities around | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - All of the above controls, - interaction risk with structures around, - mancage, cranes & lifting - Positioning the crane is critical. **Crane Corp to develop the lifting plan, - Two mancages are required - Crane Corp to provide - **Craig (COV) to develop Rescue plan - use 2-3 spotters Dropped objects: - all tools will be lanyarded - SRG to provide and ensure - bolts will be on lifting bags, which are connected to lanyards - SRG to provide and ensure | Health & Safety | Severe | Unlikely | High | 19 | High 19 | - Positioning the crane is critical. **Crane Corp to develop the lifting plan, - Two mancages are required - Crane Corp to provide - **Craig (COV) to develop Rescue plan - use 2-3 spotters Dropped objects: - all tools will be lanyarded - SRG to provide and ensure - bolts will be on lifting bags, which are connected to lanyards - SRG to provide and ensure
| R-09 | Safety | Critical | Train 1 Assembly module 2 to module 1 | Cranes & lifting - dropped objects, suspended loads, Work at Height - Dropped objects - SIMOPS - shutdown activities around | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - All of the above controls, - EWP and cranage. - Guiding the load - push pull stick and double tag line | Health & Safety | Severe | Unlikely | High | 19 | High 19
| R-10 | Safety | Critical | Train 1 Install stack pipe segments C&D | Cranes & lifting - dropped objects, suspended loads, Work at Height - Dropped objects - SIMOPS - shutdown activities around | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - All of the above controls | Health & Safety | Severe | Unlikely | High | 19 | High 19
| R-11 | Safety | Critical | Train 1 Install module 3 | Cranes & lifting - dropped objects, suspended loads, Work at Height - Dropped objects - SIMOPS - shutdown activities around | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - All of the above controls - rope access personnel - internal bolts assembly - **SRG will provide rescue plan - COV to review | Health & Safety | Severe | Unlikely | High | 19 | High 19 | - **SRG will provide rescue plan - COV to review
| R-12 | Safety | Critical | Train 1 Install segments E | Cranes & lifting - dropped objects, suspended loads, Work at Height - Dropped objects - SIMOPS - shutdown activities around | • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - All of the above controls | Health & Safety | Severe | Unlikely | High | 19 | High 19
| R-13 | Safety | Critical | Train 1 Install module 4 (already preassembled) | As above | As above | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - All of the above controls | Health & Safety | Severe | Unlikely | High | 19 | High 19
| R-14 | Safety | Critical | Train 1 Install segment F | As above | As above | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - All of the above controls | Health & Safety | Severe | Unlikely | High | 19 | High 19
| R-15 | Safety | Critical | Train 1 Install module 5 (already preassembled) | As above | As above | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - All of the above controls | Health & Safety | Severe | Unlikely | High | 19 | High 19
| R-16 | Safety | Critical | Train 1 Install segment G&H | As above | As above | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - All of the above controls | Health & Safety | Severe | Unlikely | High | 19 | High 19
| R-17 | Safety | Critical | General: Derigging modules | As above | As above | KWI | Health & Safety | Severe | Likely | Extreme | 24 | Extreme 24 | - Mancage & rope access - mancage rescue plan and rope access rescue plan - | Health & Safety | Severe | Unlikely | High | 19 | High 19
| R-18 | Safety | Operational | Injury / Incident notification | Personnel injured and require immediate response | Injured personnel not attended timely | KWI | Health & Safety | Moderate | Possible | Medium | 13 | Medium 13 | - COV to provide radios to workgroup, - COV to provide site famil, site Emergency contact number, - COV to setup a remote swipe reader box - to account for people during mustering, evacuation or Shelter in place, - COV to provide DAPs | Health & Safety | Moderate | Unlikely | Medium | 9 | Medium 9 | Craig (COV) to action: - COV to provide radios to workgroup, - COV to provide site famil, site Emergency contact number, - COV to setup a remote swipe reader box - to account for people during mustering, evacuation or Shelter in place, - COV to provide DAPs
| R-19 | Safety | Operational | Site evacuation | Personnel not accounted during evacuation or SIP | Injured personnel not attended timely | KWI | Health & Safety | Moderate | Possible | Medium | 13 | Medium 13 | as above | Health & Safety | Moderate | Unlikely | Medium | 9 | Medium 9
| R-20 | Safety | Operational | SIMOPS - Plant operations | Hazardous chemicals | Hazardous chemicals: • Critical Injury • Permanent disability • One or more fatalities | KWI | Health & Safety | Moderate | Possible | Medium | 13 | Medium 13 | - All workers must complete Site Familiarisation walks - All workers must complete Diphoterine awareness training - Notify Covalent of any hazardous chemicals brought onsite. | Health & Safety | Severe | Unlikely | High | 19 | High 19
| R-21 | Safety | Operational | [11 empty] | Health & Safety
| R-22 | Safety | Operational | [11 empty] | Health & Safety
| R-23 | Safety | Operational | [11 empty] | Health & Safety

## Matrix (hidden)
Rating | Insignificant | Minor | Moderate | Major | Severe
Almost certain | Medium | High | High | Extreme | Extreme
Likely | Medium | Medium | High | High | Extreme
Possible | Low | Medium | Medium | High | High
Unlikely | Low | Low | Medium | Medium | High
Rare | Low | Low | Low | Medium | Medium
Score | Insignificant | Minor | Moderate | Major | Severe
Almost certain | 11 | 16 | 20 | 23 | 25
Likely | 7 | 12 | 17 | 21 | 24
Possible | 4 | 8 | 13 | 18 | 22
Unlikely | 2 | 5 | 9 | 14 | 19
Rare | 1 | 3 | 6 | 10 | 15

## Lists (hidden)
Yes | Approvals | Safety | Health & Safety | Critical Risk
No | Process | Approvals | Environment | Operational Risk
| CAPEX | Environment | Regulatory
| OPEX | Engineering | Reputation
| Schedule | Process & Quality | Production Impact
| Safety | Commercial | Schedule
|  | Delivery | Financial
Mining
Commissioning & ramp up
Technology
Finance
People